## template
EPMO Go Live Readiness Assessment
Project Name |  |  |  | Go Live Date
Executive Sponsor(s) |  |  |  | Project No
System Readiness
# | Go Live Criteria - What to Measure |  | Minimal Acceptable Measures/Associated Document | Complete | Updates/ Notes
1 | Hardware build for all environments, including production, is complete
2 | Infrastructure and network build for all environments, including production, is complete
3 | Platform build for all environments, including production, is complete
4 | Security requirements implemented and approved
5 | Change freeze has been instituted after release of the latest version
List additional criteria, as needed
System Functionality
6 | All requirements have been implemented and meets agreed upon success criteria
7 | User Acceptance Testing (UAT) is complete and signed off
8 | Security role testing is complete and successful
9 | Performance testing is complete and successful
10 | Interface testing is complete and successful
11 | Additional equipment testing is complete and successful
12 | Data quality activities are agreed upon and complete
13 | Data conversion is complete and accepted by users
14 | All showstoppers and critical work items have been resolved
15 | Non-critical defects or enhancements have been identified, documented and agreed upon to be deferred
List additional criteria, as needed
Business Readiness
16 | Key users have been trained
17 | Remaining end users have been trained
18 | Changes to business processes are understood and communicated to users and stakeholders
19 | Training effectiveness has been measured and validated
20 | Training documents and resources are available to users
21 | Communication of the implementation to users and stakeholders is complete
List additional criteria, as needed
Go Live
22 | Deployment / cutover plan is in place and agreed upon
23 | Backup and restore procedures have been defined
24 | Go live support staff have been identified and are available to support users and address issues (includes external vendors, technical team, and business support)
25 | Help desk is ready to support the implementation
26 | Issue / risk management plan is in place to resolve and escalate issues
27 | Roles and responsibilities are defined to resolve issues and make decisions
28 | Plan is in place to communicate any changes and/or progress of issues during the go live period
29 | Incident tracking process is agreed upon and available to users
30 | Knowledge transfer from the project team to production support staff is complete
List additional criteria, as needed
Post-implementation Preparedness
31 | Measurable benefits are identified and approved
32 | Responsible owners are identified to measure benefits and are prepared to provide metrics
33 | Disaster recovery plan is in place
34 | Business continuity plan is in place
35 | Lessons learned meeting is scheduled after go live
List additional criteria, as needed
GO LIVE READINESS ASSESSMENT APPROVALS
The signatures below acknowledge that this document is as complete and as accurate as possible, and confirms the agreement and approval to proceed with the project Go Live
Project Role |  | Name | Title | Signature |  | Date
Project Manager
Project Manager
Executive Sponsor
Executive Sponsor
Business Sponsor
Business Sponsor
PMO Director
ITD Executive Approver
ITD Director
DRAFT

## sample
EPMO Go Live Readiness Assessment
Project Name |  |  |  | Go Live Date
Business Sponsor(s) |  |  |  | Project No
System Readiness
# | Go Live Criteria - What to Measure |  | Minimal Acceptable Measures/Associated Document | Complete | Updates/ Notes
1 | Hardware build for all environments, including production, is complete |  | The hardware for all environments are set up and ready | Yes
2 | Infrastructure and network build for all environments, including production, is complete |  | Infrastructure and network for all environments are set up and ready | Yes
3 | Platform build for all environments, including production, is complete |  | Platform for all environments are set up and ready | Yes
4 | Security requirements implemented and approved |  | Server hardening and security scan completed Security plan signed off | Yes | Completed on 2/28/20
5 | Change freeze has been instituted after release of the latest version |  | Code freeze in effect 2 weeks before go live Latest version will be deployed to production | Yes
List additional criteria, as needed
System Functionality
6 | All requirements have been implemented and meets agreed upon success criteria |  | Requirements document approved and signed off Requirements traceability documented, tested, and signed off | Yes | Requirements document signed off on 2/28/20 Change requests have been tested and signed off
7 | User Acceptance Testing (UAT) is complete and signed off |  | UAT Sign Off | Yes | UAT Sign off on 2/28/20
8 | Security role testing is complete and successful |  | Single Sign On is implemented User Access Roles documented and approved | Yes | SSO tested and validated on 2/14/20
9 | Performance testing is complete and successful |  | Performance test report reviewed | Yes
10 | Interface testing is complete and successful |  |  | No | No interfaces for Phase 1
11 | Additional equipment testing is complete and successful |  | Test plan includes testing of additional equipment Equipment test scripts results pass | Yes | Scanner equipment testing completed and passed
12 | Data quality activities are agreed upon and complete |  | Data cleansing activities completed and validated | Yes
13 | Data conversion is complete and accepted by users |  | Data conversion activities completed and validated | Yes
14 | All showstoppers and critical work items have been resolved |  | All showstoppers and critical work items resolved and tested | Yes
15 | Non-critical defects or enhancements have been identified, documented and agreed upon to be deferred |  | Issue and enhancement log(s) lists only non-critical items that are approved to be deferred after go live | Yes | Next release after go live is tentatively scheduled for 3/30/20
List additional criteria, as needed
Business Readiness
16 | Key users have been trained |  | Key users have been trained to perform their functions in the new system Training plan/schedule | Yes
17 | Remaining end users have been trained |  | End users have been trained and/or a training plan is in place to train remaining end users Training plan/schedule | Yes | Online training materials for essential functions are available on SharePoint site
18 | Changes to business processes are understood and communicated to users and stakeholders |  | End users have been trained on all new business processes Policies have been communicated and posted List updated policies | Yes
19 | Training effectiveness has been measured and validated |  | End users are able to perform business functions in the new system Training plan includes metrics to measure success | Yes
20 | Training documents and resources are available to users |  | Training resource materials are available and communicated to users | Yes | SharePoint site has training users available to users
21 | Communication of the implementation to users and stakeholders is complete |  | Project implementation has been communicated to all users and stakeholders | Yes | Communication to users in progress from 1/7/20 to present through supervisors, email, and meetings Presentation to governance committee and Sr. Leadership completed on 2/2020
List additional criteria, as needed
Go Live
22 | Deployment / cutover plan is in place and agreed upon |  | Deployment / cutover plan and/or checklist has been developed Mock deployment/cutover has been performed | Yes
23 | Backup and restore procedures have been defined |  | Backup and restore procedures are documented | Yes
24 | Go live support staff have been identified and are available to support users and address issues (includes external vendors, technical team, and business support) |  | Production support staff have been identified and are available; Contact list communicated FAQs developed and available Tiered support procedures documented | Yes
25 | Help desk is ready to support the implementation |  | Help desk has resources and verified readiness FAQs developed and available | Yes
26 | Issue / risk management plan is in place to resolve and escalate issues |  | Issue / risk management plan and log are in place | Yes
27 | Roles and responsibilities are defined to resolve issues and make decisions |  | Roles and responsibilities are clearly defined Person(s) with authority to make decisions identified | Yes
28 | Plan is in place to communicate any changes and/or progress of issues during the go live period |  | Communication method and responsible team member(s) identified to communicate changes/issue resolution | Yes | System updates will be posted on website by John Smith on daily basis upon Director approval
29 | Incident tracking process is agreed upon and available to users |  | Incident tracking is available to users to report bugs and issues | Yes | TFS will be available to production support team and help desk to report bugs
30 | Knowledge transfer from the project team to production support staff is complete |  | Knowledge transfer is complete or a plan is in place to transfer knowledge after go live | Yes
List additional criteria, as needed
Post-implementation
31 | Measurable benefits are identified and approved |  | Benefits (or transition) plan lists measurable benefits and metrics Approved benefits (or transition) plan and/or project charter | Yes
32 | Responsible owners are identified to measure benefits and are prepared to provide metrics |  | Benefits (or transition) plan lists responsible owners to measure benefits realization after go live | Yes
33 | Disaster recovery plan is in place |  | Transition plan lists disaster recovery plan | Yes
34 | Business continuity plan is in place |  | Transition plan lists business continuity plan | Yes
35 | Lessons learned meeting is scheduled after go live |  | Lessons learned document | Yes | Lessons learned scheduled for 3/14/2020
List additional criteria, as needed
GO LIVE READINESS ASSESSMENT APPROVALS
The signatures below acknowledge that this document is as complete and as accurate as possible, and confirms the agreement and approval to proceed with the project Go Live
Project Role |  | Name | Title | Signature |  | Date
Project Manager
Project Manager
Executive Sponsor
Executive Sponsor
Business Sponsor
Business Sponsor
PMO Director
ITD Executive Approver
ITD Director
DRAFT